## Estimation Gudielines
1 | You need to consider following color codes for the resepctive technology estimates [BA will take care of this.]
| Backend (PHP/.NET/JAVA/NODE) | #d9e1f2
| Design | #dab7f7
| HTML | #d0cece
| JS Frontend (Angular JS / React JS / Vue JS) | #a7f7fa
| Native Android | #ffc000
| Native IOS | #86adf7
| Hybrid Mobile (ReactNative / Xamrine) | #a9d08e
2 | 8 hours per day need to consider while giving the estimations.
3 | The "Is Unique" column is useful for the graphic designer. will help them to understand unique pages for design.
4 | If any feature/task requires more than 40 hours then it should be breakdown into a subfeatures / subtasks.
5 | Do not copy anything from UD as a assumptions. Purpose of the assumptions to limit your scope within your estimated numbers. ("This much only i have consider for this effort")
`

## WBS-Master
[5 empty] | Graphics |  |  | HTML |  | Frontend (Razor Forms) (.Net Core MVC) |  | (C# .NET Core API) (Rest Based) |  | MOBILE (React Native / Xamrin ) |  | Mobile (IOS) |  | Mobile (Android)
Sr. No. | Interface | Modules/Sub Modules | Features / Tasks | Assumptions | Is Unique | Estimation (Hours) | Assumptions / Remarks | Estimation (Hours) | Assumptions / Remarks | Estimation | Assumptions / Remarks | Estimation | Assumptions / Remarks | Estimations | Assumptions / Remarks | Estimations | Assumptions / Remarks | Estimations | Assumptions / Remarks
| Project Setup |  |  | As discussed with SA team, we will have service oriented architecture for this, where we will have REST based API and front end as MVC. Cutomer have plan to have mobile application in future |  | 8 | understanding | 8 | Project setup and theme setup | 40 | Setup architecture, general & common utilities for project | 60 | Setup architecture, general & common utilities for project
ERP/CRM integration is not considered in this estimation, as mentioned in scope ERP/Existing CRM integration will be in phase 2
1 | Super Admin User (Custom) | Login | User will be login into the application with given username / password. | considering 1 page with user name and password text inputs |  | 4 | considering 1 page with user name and password text inputs | 9 |  | 8 | We will have service oriented architecture, so token based system will be there | 16
|  | Forget Password |  | considerng 2 page with option of enter email and reset password |  | 4 | considerng 2 page with option of enter email and reset password |  |  | 8 |  | 12
|  | Dashboard | to view the overview of the proposal status, revenue generation, project performance, Management details, client details and analyst details. | Assuming we will have mostly tabular data & some bar / pie charts |  | 18 | considering 2 option with one iteration, No any graphcs included | 30 | to view the overview of the proposal status, revenue generation, project performance, Management details, client details and analyst details. | 18 | Assuming we will have mostly tabular data & some bar / pie charts | 24
|  | Manage Department | User will be able to create / edit/ view /active / de active the department details. There will be 5-10 text fields. and user will be able to view it | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns |  | 8 | considering 3 to 4 page as list view, detail view, where user can able to create / edit/ view /active / de active the acess permision | 15 | User will be able to create / edit/ view /active / de active the department details. There will be 5-10 text fields. and user will be able to view it | 8 | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns | 10
|  | Manage Sub Admin | User will be able to create / edit/ view /active / de active the Sub admin details. There will be 5-10 text fields. and user will be able to view it | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns |  | 5 | considering the same design manage department with change in data | 8 | considering the same design manage department with change in data | 8 | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns | 10
|  | Roles and Access Permissions | User will be able to create / edit/ view /active / de active the roles and access permission details. |  |  | 5 | considering 3 to 4 page as create / edit/ view /active / de active the acess permision | 8 |  | 12 |  | 20
| Valuation Process | Master
|  | Location | User will be able to create / edit/ view /active / de active / search the created location details. | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns |  | 8 | considering the same design manage department with change in data with cosmetic support | 5 | Using the same design super admin Manage Department 5/7 fields entry form and will have only 1/2 cascade dropdowns | 6 | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns | 8
|  | Client | User will be able to create / edit/ view /active / de active / search the client details. | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns |  |  |  | 4 | Considerign 5/7 fields entry form and will have only 1/2 cascade dropdowns | 8 | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns | 10
|  | External Vendors | User will be able to create / edit/ view /active / de active / search the created external vendor details. | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns |  |  |  | 3 | Comsidering with 5/7 fields entry form and will have only 1/2 cascade dropdowns | 8 | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns | 10
|  | Projects | User will be able to create / edit/ view /active / de active / search the created project details. | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns |  |  |  | 0 | Re-use same as above | 8 | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns | 12
|  | Valuation Approver | User will be able to create / edit/ view /active / de active / search the created valuation approver details. | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns |  |  |  | 0 | Re-use same as above | 8 | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns | 10
|  | External Valuation Approver | User will be able to create / edit/ view /active / de active / search the created external valuation approver details. | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns |  |  |  | 0 | Re-use same as above | 8 | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns | 10
|  | History | User will be able to create / edit/ view /active / de active / search the created history details. | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns |  |  |  | 0 | Re-use same as above | 8 | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns | 10
|  | Currency | User will be able to create / edit/ view /active / de active / search the currency details. | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns |  |  |  | 0 | Re-use same as above | 6 | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns | 8
|  | Approval Master | User will be able to create / edit/ view /active / de active / search the approval master details. | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns |  |  |  | 0 | Re-use same as above | 8 | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns | 10
|  | Valuation Request creation |  |  |  | 0 |  | 0 | Re-use same as above | 8 | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns | 16
|  | View created Request with Approval / Rejection (Approver 1) | page which includes list and detail view with the option of approve , reject ,notes and search option |  |  | 4 | considering 2 to 3 page which includes list and detail view with the option of approve , reject ,notes and search option | 9 |  | 8 |  | 16
|  | View created Request with Approval / Rejection (Approver 2) | page which includes list and detail view with the option of approve , reject ,notes and search option |  |  | 0 |  | 0 | Same design as Approver | 8 |  | 12
|  | Manage Quotation | 2 to 3 page which includes list view,create, edit,view details,search . | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns |  | 5 | considering 2 to 3 page which includes list view,create, edit,view details,search . It will similar layouts for all the pages | 6 |  | 8 | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns | 16 | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns
|  | Manage Payment | Manage Invoice and Receiptwere user can view list view, detail of payment and reciept generation of payment |  |  | 6 | considering 3 to 4 page were user can view list view, detail of payment and reciept generation of payment | 9 |  | 16 |  | 24
|  | Terms of Engagement | User will be able to add / view the terms of engagement details.share via mail alonmg with proposal |  |  | 5 | considering 2 to 3 page as list , detail of terms which includes add, edit and search option | 7 |  | 12 |  | 12
|  | Evaluation Process | [7 empty] | 12 |  | 12
|  | Valuation Instructor Screen | View detail page with the status of valuation |  |  | 3 | considering detail page with the status of valuation | 5 |  | 12 |  | 12
|  | Site Description Screen | User will be able to create / edit/ view /delete the site description details. |  |  | 2 | considering the same design manage department with change in data | 5 |  | 12 |  | 12
|  | Comparable Evidences | User will be able to create / edit/ view /delete the evidence details and upload relevant documents |  |  | 4 | considering 2to3 page which includes list view, detail view,add,edit,delete,search and upload option | 5 |  | 12 |  | 12
|  | Valuation Assessment | User will be able to create / edit/ view /delete the assessment details and upload relevant documents |  |  | 2 | considering the same design manage department with change in data | 5 |  | 10 |  | 12
|  | Relevant Documents | User will be able to upload / view /delete the document details. |  |  | 4 | considering 2 to 3 screen where user upload, view and delete document | 5 |  | 10 |  | 12
|  | View valuation Request Internal Approval / Rejection | User will be able to view / approve / reject the valuation request details along with status and approver name / email and notes. |  |  | 4 | considering 2 to 3 screen with option of accept, reject,list and detail page | 5 |  | 10 |  | 12
|  | Notifications | User will be able to view the notifications related to creation approval status and other notification if any. |  |  | 2 | considered pop up for notification | 5 |  | 28 |  | 24
|  | Reports | User will be able to view the 10 – 15 reports based on the process and projects. | Assuming maximum 10/12 reports with having mostly tabular data |  | 4 | considering tabular structure for report will provide only 2 in design | 9 | only 2 Reports considering other rest of similer for reuse | 60 | Assuming maximum 10/12 reports with having mostly tabular data | 60 | Assuming maximum 10/12 reports with having mostly tabular data
|  | Log out |  |  |  | 0 | amusing log out leads to login page | 0 |  | 2 |  | 4
4 | Others | Document Automation Works | • User will be able to upload/import document in from of PDF, JPEG, JPG, and Word formats. • We will fetch Data/Details from the uploaded documents as per certain criteria/parameters. This ensures that we will fetch selective data to the system and not the whole document as is • User will be able to view data, update data, delete data • User will be able to further extract/export selected data to PDF, CSV and Excel document format. Note: • We assume document details/data in the source format will have a predefined structure. We will consider predefined format document to be processed to further generate readable data on the system. • We will only support certain data formats for import and export - PDF, JPEG, JPG, and Word for import and PDF, CSV, Excel format for export • User will not be able to add additional fields. • Exported data will be viewed in a Tabular/Grid format. | otification |  | 12 | Considerig 6 -8 pages like view data, update data, delete data | 20 |  | 40 |  | 60
|  | SMS Integration | [7 empty] | 0 |  | 24
|  | Email Integration | [7 empty] | 0 |  | 24
|  | English and Arabic Language | [5 empty] | 60 | Considering English and Arabiic for both, user and super admin with mobile responisve | 40 |  | 40
|  | Payment Gateway Integration | [7 empty] | 0 |  | 60
|  | Mobile Responisve |  |  |  | 20 | Considering 5 - 7 Unique screens only.
|  | After Inegration support | [5 empty] | 40 | After Inegration support
|  | Testing | Issues & bug fixing
|  | assets sharing |  |  |  | 8
|  | Presentation |  |  |  | 6
|  | ui guideline |  |  |  | 6
|  | Number of hours |  |  |  | 157 |  | 285 |  | 478 |  | 716
|  | Number of days |  |  |  | 19.625 |  | 35.625 |  | 59.75 |  | 89.5
|  | Number of weeks |  |  |  | 3.925 |  | 7.125 |  | 11.95 |  | 17.9

## Resource Structure
# | Resource Type | No. of Resource | Weeks | Total | Given By | Approved By | Comment
1 | Graphic | 1 | 3.9 | 3.9 | varun
2 | HTML | 1 | 7.1 | 7.1 | Viren
3 | .NET MVC (Front end) | 1 | 11.9 | 11.9 | Nilesh
4 | .NET API (backend) | 1 | 17.9 | 17.9 | Nilesh |  | Service oriented architecture will be there
5 | BA | 2 | 6 | 12 | Amol
6 | Devops | 1 | 6.4 | 6.4 | Swapnil Shingote
7 | SA | 1 | 4 | 4 | Swapnil Waghela

## (Revised)EOREMAD_Gantt_Char V1
For Proposal
SDLC | Weeks / Activities | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32
Requirement Gathering | bar: W1 to W8
Devops | bar: W8 to W11; W28 to W30
Design | bar: W6 to W10
Development | bar: W10 to W25
QA - Test Plan & Test Cases | bar: W10 to W13
QA - Testing | bar: W20 to W25
UAT | bar: W26 to W28
UAT Sign off | bar: W29
Production Deployment | bar: W29 to W30
Training | bar: W31 to W32
For Internal Purpose | Resource Loading | [32 empty] | Man Weeks
PM | PM | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 16.5
BA | BA 1 | [32 empty] | 6 | bar: W1 to W6
| BA 2 | [32 empty] | 6 | bar: W3 to W8
Graphics Designer | Designer | [32 empty] | 4 | bar: W6 to W10
TL | Architect 1 | [6 empty] | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [5 empty] | 12.5
HTML Designer | HTML Designer | [32 empty] | 8 | bar: W9 to W16
.NET Core | Dev 1 | [32 empty] | 15 | bar: W10 to W24
| Dev 2 | [32 empty] | 15 | bar: W11 to W25
QA | Manual Tester 1 | [32 empty] | 10 | bar: W10 to W13; W20 to W25
UAT | .Net Dev 1 | [32 empty] | 3 | bar: W26 to W28
| HTML | [32 empty] | 3 | bar: W26 to W28
| Tester | [32 empty] | 3 | bar: W26 to W28
Deployment | Devops | [32 empty] | 7 | bar: W8 to W11; W28 to W30
Training | BA | [32 empty] | 2 | bar: W31 to W32
Delivery Excellence | [33 empty] | 8
| Total | [32 empty] | 119
30