## Slide 1
Completed Level-I of wireframes, SRS document and sent it to Karuna after working on wireframes, requirement gathering with both BA teams.
Working on Karuna suggested wireframe changes, SRS documents from 3rd April discussion
Planned meeting on wireframes, SRS document review with stakeholder on 6th Apr.
Will discuss Angular UI technology adoption with stake holders in 6th Apr meeting.
Planned Key Milestones
Milestone Legend
Eltizam - Real Estate Valuation System
Planning to completed all review suggested changes on wireframes, SRS documents.
Also, planning to start Graphical & HTML once wireframes are freezes.
Once UI tech stacks finalized then, we will start CICD, SA related task in coming 1-2 weeks.
Accomplishment for the week
Status update for the week - 3rd April to 6th April 2023
Phase | Planned Start date | Planned End date | Actual Start date | Actual End date
Kick-Off | 9-Mar-23 | 9-Mar-23 | 9-Mar-23 | 9-Mar-23
Req. Gather, SRS writing | 10-Mar-23 | 22-May-23 | 13-Mar-23 | 
Wireframes | 27-Mar-23 | 22-May-23 | 20-Mar-23 | 
Graphic integration | 24-Apr-23 | 24-May-23 |  | 
Themes integration | 24-Apr-23 | 23-Jun-23 |  | 
Development | 1-May-23 | 8-Sep-23 |  | 
Testing | 19-Jun-23 | 8-Sep-23 |  | 
UAT release | 11-Sep-23 | 22-Sep-23 |  | 
Production release | 25-Sep-23 | 26-Sep-23 |  | 
Training | 27-Sep-23 | 10-Oct-23 |  | 
We have submitted Wireframes, SRS document to Karuna & yet to receive feedback from Eltizam business.
Key Risks
PM : YallaReddy
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Need to get wireframes approvals on time to make sure no other additional or rework requires.
Maintenance | 10-Oct-23 | - |  |