## Slide 1
Received signoff email to start design, development only for master modules.
Started desing for Login, User list, edit pages.
Discussed and submitted primary design pages to Eltizam team for review and approval.
Planned Key Milestones
Milestone Legend
Eltizam - Real Estate Valuation System
Will do design of UI/UX for the projectt on other pages.
Also, keep in touch with BA to get final requirements on Evaluation module.
We will start HTML design after requirements finalized to avoid rework.
Accomplishment for the week
Status update for the week - 17th to 21st July, 2023
Phase | Planned Start date | Planned End date | Actual Start date | Actual End date
Kick-Off | 9-Mar-23 | 9-Mar-23 | 9-Mar-23 | 9-Mar
Requirement Gathering | 10-Mar-23 | 22-May-23 | 13-Mar-23 | 
Wireframes | 27-Mar-23 | 22-May-23 | 20-Mar-23 | 
SRS Document | 1-May-23 | 26-May-23 | 23-May23 | 
Graphic integration | 24-Apr-23 | 24-May-23 | 17-Jul-2023 | 
Themes integration | 24-Apr-23 | 23-Jun-23 |  | 
Development | 1-May-23 | 8-Sep-23 |  | 
Testing | 19-Jun-23 | 8-Sep-23 |  | 
UAT release | 11-Sep-23 | 22-Sep-23 |  | 
Production release | 25-Sep-23 | 26-Sep-23 |  | 
Training | 27-Sep-23 | 10-Oct-23 |  | 
Warranty | 10-Oct-23 | 07-Nov-23 |  | 
Still waiting for Evaluation process requirement changes.
Started design for master modules from this week
Key Risks
PM : YallaReddy
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Need to receive final feedback on wireframes from End-client.
As of now, project is delayed by 7 weeks, so please do needful by giving reviews on wireframes.