## Slide 1
HTML Developer understood pages flow and started integrating them to HTML tables.
API team started created tables and API base preparations from 13th September.
Submitted mind map diagram to Karuna from BA which gives overall project flow.
Planned Key Milestones
Milestone Legend
Eltizam - Real Estate Valuation System
HTML developer will start merge his changes into .NET application once Resource page is done.
API team will continue working login, resource master pages with design integrations.
Accomplishment for the week
Status update for the week - 11th Sept to 15th Sept, 2023
Phase | Planned Start date | Planned End date | Actual Start date | Actual End date
Kick-Off | 09-03-23 | 9-03-23 | 9-03-23 | 9-03-23
Requirement Gathering | 10-03-23 | 22-05-23 | 13-03-23 | 11-8-23
Wireframes | 27-03-23 | 22-05-23 | 20-03-23 | 11-8-23
SRS Document | 01-05-23 | 26-05-23 | 23-05-23 | 23-8-23
Graphic integration | 24-Apr-23 | 24-05-23 | 17-07-23 | 23-8-23
Themes integration | 24-Apr-23 | 23-Jun-23 | 11-09-23 | 
Development | 1-May-23 | 8-Sep-23 | 13-09-23 | 
Testing | 19-Jun-23 | 8-Sep-23 |  | 
UAT release | 11-Sep-23 | 22-Sep-23 |  | 
Production release | 25-Sep-23 | 26-Sep-23 |  | 
Training | 27-Sep-23 | 10-Oct-23 |  | 
Warranty | 10-Oct-23 | 07-Nov-23 |  | 
Kick-off on 9th March 2023, Requirement Gathering from 10th Mar to 23rd Aug.
Designer started from 17th July & submitted all design on 23rd Aug.
HTML integration & .NET Development started from 13th Sept 2023.
Key Risks
PM : YallaReddy
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
As of now, project is delayed by 12 weeks due to delay in initial phase of RG.