## Slide 1
Worked on design integration for some of the master pages.
Completed all master modules for API with changes from review.
Completed Resources, Login, Client, Location, Roles, Designation, Department, Project Type, Project Sub Type masters.
Worked on rendering pages depends on role access are done.
Planned Key Milestones
Milestone Legend
Eltizam - Real Estate Valuation System
Will continue working on HTML development this week as well.
Will complete all master modules this week and then will start Evaluation modules.
We will show ready pages on Thursday call.
Accomplishment for the week
Status update for the week - 9th Oct to 13th Oct, 2023
Phase | Planned Start date | Planned End date | Actual Start date | Actual End date
Kick-Off | 09-03-23 | 9-03-23 | 9-03-23 | 9-03-23
Requirement Gathering | 10-03-23 | 22-05-23 | 13-03-23 | 11-8-23
Wireframes | 27-03-23 | 22-05-23 | 20-03-23 | 11-8-23
SRS Document | 01-05-23 | 26-05-23 | 23-05-23 | 23-8-23
Graphic integration | 24-Apr-23 | 24-05-23 | 17-07-23 | 23-8-23
Themes integration | 24-Apr-23 | 23-Jun-23 | 11-09-23 | 10-11-23
Development | 1-May-23 | 8-Sep-23 | 13-09-23 | 30-11-23
Testing | 19-Jun-23 | 8-Sep-23 | 11-1-23 | 10-12-23
UAT release | 11-Sep-23 | 22-Sep-23 | 1-12-23 | 10-12-23
Production release | 25-Sep-23 | 26-Sep-23 | 11-12-23 | 11-12-23
Training | 27-Sep-23 | 10-Oct-23 |  | 
Warranty | 10-Oct-23 | 07-Nov-23 |  | 
Kick-off on 9th March 2023, Requirement Gathering from 10th Mar to 23rd Aug.
Designer started from 17th July & submitted all design on 23rd Aug.
HTML integration & .NET Development started from 13th Sept 2023.
Currently master modules are going for both API, front design integrations.
Key Risks
PM : YallaReddy
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
As of now, project is delayed by 12 weeks due to delay in initial phase of RG. .
We are targeting to delivery project in first half of Dec 2023.