## Slide 1
www.neosofttech.com
+91 22 40500600
sales@neosofttech.com
Project Kick-off
Presentation
20-May-2022
A SEI-CMMi Level-5 Global IT Consulting & Software Solutions Provider

## Slide 2
Project Overview / Scope
Solution Architecture
Technology Stacks
Work Breakdown Structure
Project Timelines
Implementation Methodology
Project Schedule
Risk & Dependencies
Key Assumptions & Constraints
Deliverables
Communication Plan
Governance Model
Escalation Procedure
Q & A
Agenda

## Slide 3: Project Overview/ Scope
Eltizam wants to develop a web application to manage the process of valuation & Evaluation process with dashboard and reports. On this application we have Super Admin user who can manage the entire process as valuation process, financial management, manage quotation, invoices, Masters, dashboards and reports. We have three levels of approvals for each process that will manage with roles and access permissions. Only admin Web application is needed in this scope. Needs to include document management with AI/suitable tools for reading data from file and display on portals.
The platform will have below entities and interfaces:
  Super Admin Users – Web Panel

## Slide 4: Solution Architecture
Note: It may need some revision basis
on requirement analysis (BA) phase.

## Slide 5: Work Breakdown Structure
Sr No. | Interface | Modules/Sub Modules
1 | Common Modules | Project Setup
2 | Super Admin User [Web] | Environment Setup and Database Design
3 | Dashboard [Web] | Design Integration
4 | Master data for different module [Web] | Role-based access control setup
5 | Valuation process[Web] | Suggested - SSO based login
6 | Evaluation Process [Web] | Login/ Logout
7 | Manage Quotations [Web] | Logout/Forgot password/ Password Setup
8 | Document management [Web] | Roles
9 | Management of Users, Sub Admins, Role & Permissions [Web] | Master modules Management
 |  | Location
 |  | External Vendors
 |  | Projects
 |  | Valuation Approver
 |  | External Valuation Approver
 |  | History
 |  | Currency
 |  | Approval Master

## Slide 6: Work Breakdown Structure
Sr No. | Interface | Modules/Sub Modules
 |  | Valuation Request creation
 |  | View created Request with Approval / Rejection (Approver 1)
 |  | View created Request with Approval / Rejection (Approver 2)
 |  | Manage Quotation
 |  | Manage Payment
 |  | Terms of Engagement
 |  | Evaluation Process
 |  | Notifications
 |  | Site Description Screen
 |  | Comparable Evidences
 |  | Reports
 |  | Relevant Documents
 |  | Document automation work

## Slide 7: Project Timelines

## Slide 8: Delivery Methodology – Hybrid Waterfall Model
Design
Maintenance
Requirements
Verification
Implementation
Feedback
Test
Scrum
Deploy
Design
Build
Single Sprint
Requirement Gathering Phase: All requirements will be analyzed and signed off
Change Management Process: Any new additional requirements identified as part of the iterative releases will be considered as change
Each Iteration: It will have multiple releases which comprises design, development, and testing phases
Iterative Delivery Approach: Early access is provided to Eltizam during SDLC ensuring the app is being developed as expected using Hybrid Approach
Core application is built, and components are added to it as part of each sprint, permitting gradual implementation
After completion of all models, integration testing and subsequently final build will be available for customer UAT

## Slide 9: Project Schedule
Note: This is a tentative schedule. Once the requirements are baselined, the actual project schedule and dates shall be submitted.

## Slide 10: Deliverables
Requirement Gathering
  SRS
  Wireframes
Design
  Theme Finalization & Integration
Project Execution
  Project Plan
  Project Monitoring Artifacts
  Risk Analysis
Development / Implementation
  Application Build
QA
  Test Plan
  Test Cases / Report
UAT
Training
  User Manual

## Slide 11: Risks and Dependencies
Sr. No. | Risk | Impact | Severity | Mitigation strategy | Owner
1 | Availability of servers/ licenses on time for initiating project | Project Initiating | High | Necessary environment to be available during the implementation phase | Eltizam
2 | Scope creep | Overall Project | High | Changes in scope due to requirements gathering phase will be re-estimated and in case extra effort are encountered, NeoSOFT will issue a change request | Eltizam, NeoSOFT
3 | Delays in getting approvals | Overall Project | High | Approval committee calendar will be set to book the timing according to the milestones | Eltizam
4 | Miscommunications/ delay in clarifications | Overall Project | High | Identify SPOC for queries clarifications. To have communication matrix to ensure all the queries are properly clarified on time. | Eltizam, NeoSOFT
5 | New additional requirements in the scope of work | Overall Project | High | If the new scope requires additional cost and time, then escalation to be done. After escalation, all parties work towards achieving timely decision and mitigation to follow decision. | Eltizam
6 | Lack of knowledge in the existing environment | Assessment Time | High | To have a proper KT Process and the availability of a SPOC for KT. | Eltizam

## Slide 12: Key Assumptions and Constraints
Exact requirements for the solution hierarchy shall be gathered in the Requirements Gathering phase
Changes in scope due to requirements gathering phase shall be re-estimated and in case extra effort are encountered, NeoSOFT system shall issue a change request
Web Applications will support the English language only.
We are considering 3rd party theme-based design for the web application.
All the 3rd Party APIs those would be integrated with the proposed system will be finalized before the start of the development. (Development time will be calculated based on the number of 3rd Party APIs and complexity of the same). Cost to be paid by the Eltizam for integrations.
The email gateway will be finalized during the requirements (BA) phase.
Responsive designs shall be implemented only if the purchased theme supports the same.
Azure will be used only as hosting environment and no other Azure services to be utilized as such.
Note: Detailed assumptions, constraints and standard terms & conditions are available in the approved proposal

## Slide 13: Communication Plan
Information | Frequency | Responsibility | Audience | Medium
Status Meetings | Weekly | PM | Key Stakeholders (Eltizam and NeoSOFT) | Email, Phone/ Teams/ Skype
Steering Committee Meeting | upon each Milestone or as and when required | PM | Key Stakeholders, Steering Committee | Email, Phone/ Teams/ Skype
Approvals | As and when required | Eltizam PM | Eltizam stake holders | Emails
Sprint review Meetings | Biweekly (Every 2 Weeks) | PM | Key Stakeholders (Eltizam and NeoSOFT) | Phone/ Teams/ Skype
Standup Meeting* | Every day (Till the discovery phase is completed) | Eltizam + NeoSOFT (PM/ BA) | Key Stakeholders (Eltizam and NeoSOFT) | Phone/ Teams/ Skype
Note: During the requirement gathering phase, we need the availability of all the key stakeholders from each
department atleast of couple of hours everyday. Will be sharing the Requirements gathering plan separately.

## Slide 14: Governance Model
Eltizam Executive Management/ Program Sponsor
NeoSOFT Executive
Team/ Head Business Unit
Eltizam Program Manager/
Business Manager
Eltizam Project
Manager
Strategic Planning
Executive Review
Dispute Resolution
Contract Amendment
Policy and Procedure Definition
Delivery Management
Performance Evaluation
Issue Resolution
Resources Management
Relationship Management
Project Management
Issue Resolution
Release Planning
Change Management
Continuous Improvement
NeoSOFT Project
Manager
NeoSOFT Delivery Head/ Program Manager
Executive Board
Engagement
Ownership
Program Management
Office
Process
Ownership
Project Management
Team
Execution
Ownership
Eltizam

## Slide 15: Escalation Procedure
Sr. No. | Description | Client Contact | NeoSOFT Contact | Name | Email
1 | Sales & Account Management | Procurement Manager | Business Development Manager |  | 
2 | Requirement Gathering | Lead Business Analyst | Lead Business Analyst | Akshatha Shinde | akshatha.shinde@neosoftmail.com
3 | Day-to-day issue resolution | Project Manager | Project Manager | YallaReddy | yalla.reddy@neosofttech.com
4 | Critical escalation when issues may impact business performance | Operations Head | VP – Delivery | Karthik N | karthik.natarajan@neosofttech.com
5 | Extended Support | Operations Head | VP – Delivery/ Solutions/ Technology | Santhosh K R | santhosh.r@neosofttech.com

## Slide 16
A
Q
&