## Estimation Gudielines
1 | You need to consider following color codes for the resepctive technology estimates [BA will take care of this.]
| Backend (PHP/.NET/JAVA/NODE) | #d9e1f2
| Design | #dab7f7
| HTML | #d0cece
| JS Frontend (Angular JS / React JS / Vue JS) | #a7f7fa
| Native Android | #ffc000
| Native IOS | #86adf7
| Hybrid Mobile (ReactNative / Xamrine) | #a9d08e
2 | 8 hours per day need to consider while giving the estimations.
3 | The "Is Unique" column is useful for the graphic designer. will help them to understand unique pages for design.
4 | If any feature/task requires more than 40 hours then it should be breakdown into a subfeatures / subtasks.
5 | Do not copy anything from UD as a assumptions. Purpose of the assumptions to limit your scope within your estimated numbers. ("This much only i have consider for this effort")
`

## WBS-Angular-v2
[5 empty] | Graphics |  |  | HTML |  | Frontend Angular |  | (C# .NET Core API) (Rest Based) |  | MOBILE (React Native / Xamrin ) |  | Mobile (IOS) |  | Mobile (Android)
Sr. No. | Interface | Modules/Sub Modules | Features / Tasks | Assumptions | Is Unique | Estimation (Hours) | Assumptions / Remarks | Estimation (Hours) | Assumptions / Remarks | Estimation | Assumptions / Remarks | Estimation | Assumptions / Remarks | Estimations | Assumptions / Remarks | Estimations | Assumptions / Remarks | Estimations | Assumptions / Remarks
| Project Setup |  | Basic setup which include GIT setup, project setup and environment configuration. Project setup include alert message setup. | [6 empty] | 16
|  |  | Role management | [6 empty] | 16 | Implementation of authguard and secure the routes based on the roles in application
|  |  | In app notification setup | [6 empty] | 16 | Firebase or any other platform integration for push notification in application. Estimations may vary based on the selection of the third party service for notification
|  |  |  | As discussed with SA team, we will have service oriented architecture for this, where we will have REST based API and front end as MVC. Cutomer have plan to have mobile application in future |  | 8 | understanding | 8 | Project setup and theme setup |  |  | 60 | Setup architecture, general & common utilities for project
|  |  |  | ERP/CRM integration is not considered in this estimation, as mentioned in scope ERP/Existing CRM integration will be in phase 2 | [5 empty] | NA | NA
1 | Super Admin User (Custom) | Login | User will be login into the application with given username / password. | considering 1 page with user name and password text inputs |  | 4 | considering 1 page with user name and password text inputs | 9 |  | 8 | Simple username and password base login is considered. If requires any OAuth login implementation then estimates will be addtional | 16
|  | Change Password | [7 empty] | 4 | New password and confirm password field is considered with all required validations
|  | Forget Password |  | considerng 2 page with option of enter email and reset password |  | 4 | considerng 2 page with option of enter email and reset password |  |  | 8 | Email or Mobile Id field suing which user can change the password | 12
|  | Dashboard | overview of the proposal status, revenue generation, project performance, Management details, client details and analyst details | [6 empty] | 8 | Display the status and respected data in text or numerical format. If details are in tabular format then time may vary
|  |  | Graphical data | [6 empty] | 28 | Pie, tabular and bar chart visualization is considered here. Estimated may vary based on the complex logic if any for chart
|  |  | to view the overview of the proposal status, revenue generation, project performance, Management details, client details and analyst details. | Assuming we will have mostly tabular data & some bar / pie charts |  | 18 | considering 2 option with one iteration, No any graphcs included | 30 | to view the overview of the proposal status, revenue generation, project performance, Management details, client details and analyst details. |  |  | 24
|  | Manage Department | List view | [6 empty] | 16 | List view of department with search and pagination
|  |  | create/ edit/ update View | [6 empty] | 24 | Same component for create/ edit and view. 5-6 textual and drop down fields are considered with all required validations and API integration
|  |  | User will be able to create / edit/ view /active / de active the department details. There will be 5-10 text fields. and user will be able to view it | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns |  | 8 | considering 3 to 4 page as list view, detail view, where user can able to create / edit/ view /active / de active the acess permision | 15 | User will be able to create / edit/ view /active / de active the department details. There will be 5-10 text fields. and user will be able to view it |  |  | 10
|  | Manage Sub Admin | List view | [6 empty] | 10 | List view of department with search and pagination
|  |  | create/ edit/ update View | [6 empty] | 16 | Same component for create/ edit and view. 5-6 textual and drop down fields are considered with all required validations and API integration
|  |  | User will be able to create / edit/ view /active / de active the Sub admin details. There will be 5-10 text fields. and user will be able to view it | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns |  | 5 | considering the same design manage department with change in data | 8 | considering the same design manage department with change in data |  |  | 10
|  | Roles and Access Permissions | List view | [6 empty] | 10 | List view of department with search and pagination
|  |  | create/ edit/ update View | [6 empty] | 16 | Same component for create/ edit and view. 5-6 textual and drop down fields are considered with all required validations and API integration
|  |  | User will be able to create / edit/ view /active / de active the roles and access permission details. |  |  | 5 | considering 3 to 4 page as create / edit/ view /active / de active the acess permision | 8 |  |  |  | 20
| Valuation Process | Master
|  | Location | List view | [6 empty] | 10 | List view of department with search and pagination
|  |  | create/ edit/ update View | [6 empty] | 16 | Same component for create/ edit and view. 5-6 textual and drop down fields are considered with all required validations and API integration
|  |  | User will be able to create / edit/ view /active / de active / search the created location details. | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns |  | 8 | considering the same design manage department with change in data with cosmetic support | 5 | Using the same design super admin Manage Department 5/7 fields entry form and will have only 1/2 cascade dropdowns |  |  | 8
|  | Client | List view | [6 empty] | 10 | List view of department with search and pagination
|  |  | create/ edit/ update View | [6 empty] | 16 | Same component for create/ edit and view. 5-6 textual and drop down fields are considered with all required validations and API integration
|  |  | User will be able to create / edit/ view /active / de active / search the client details. | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns |  |  |  | 4 | Considerign 5/7 fields entry form and will have only 1/2 cascade dropdowns |  |  | 10
|  | External Vendors | List view | [6 empty] | 10 | List view of department with search and pagination
|  |  | create/ edit/ update View | [6 empty] | 16 | Same component for create/ edit and view. 5-6 textual and drop down fields are considered with all required validations and API integration
|  |  | User will be able to create / edit/ view /active / de active / search the created external vendor details. | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns |  |  |  | 3 | Comsidering with 5/7 fields entry form and will have only 1/2 cascade dropdowns |  |  | 10
|  | Projects | List view | [6 empty] | 10 | List view of department with search and pagination
|  |  | create/ edit/ update View | [6 empty] | 16 | Same component for create/ edit and view. 5-6 textual and drop down fields are considered with all required validations and API integration
|  |  | User will be able to create / edit/ view /active / de active / search the created project details. | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns |  |  |  | 0 | Re-use same as above |  |  | 12
|  | Valuation Approver | List view | [6 empty] | 10 | List view of department with search and pagination
|  |  | create/ edit/ update View | [6 empty] | 16 | Same component for create/ edit and view. 5-6 textual and drop down fields are considered with all required validations and API integration
|  |  | User will be able to create / edit/ view /active / de active / search the created valuation approver details. | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns |  |  |  | 0 | Re-use same as above |  |  | 10
|  | External Valuation Approver | List view | [6 empty] | 10 | List view of department with search and pagination
|  |  | create/ edit/ update View | [6 empty] | 16 | Same component for create/ edit and view. 5-6 textual and drop down fields are considered with all required validations and API integration
|  |  | User will be able to create / edit/ view /active / de active / search the created external valuation approver details. | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns |  |  |  | 0 | Re-use same as above |  |  | 10
|  | History | List view | [6 empty] | 10 | List view of department with search and pagination
|  |  | create/ edit/ update View | [6 empty] | 16 | Same component for create/ edit and view. 5-6 textual and drop down fields are considered with all required validations and API integration
|  |  | User will be able to create / edit/ view /active / de active / search the created history details. | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns |  |  |  | 0 | Re-use same as above |  |  | 10
|  | Currency | List view | [6 empty] | 10 | List view of department with search and pagination
|  |  | create/ edit/ update View | [6 empty] | 16 | Same component for create/ edit and view. 5-6 textual and drop down fields are considered with all required validations and API integration
|  |  | User will be able to create / edit/ view /active / de active / search the currency details. | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns |  |  |  | 0 | Re-use same as above |  |  | 8
|  | Approval Master | List view | [6 empty] | 10 | List view of department with search and pagination
|  |  | create/ edit/ update View | [6 empty] | 16 | Same component for create/ edit and view. 5-6 textual and drop down fields are considered with all required validations and API integration
|  |  | User will be able to create / edit/ view /active / de active / search the approval master details. | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns |  |  |  | 0 | Re-use same as above |  |  | 10
|  | Valuation Request creation | List view | [6 empty] | 12 | List view of department with search and pagination
|  |  | create/ edit/ update View | [6 empty] | 24 | Same component for create/ edit and view. 18-29 textual and drop down fields are considered with all required validations and API integration
[6 empty] | 0 |  | 0 | Re-use same as above |  |  | 16
|  | View created Request with Approval / Rejection (Approver 1) | page which includes list and detail view with the option of approve , reject ,notes and search option |  |  | 4 | considering 2 to 3 page which includes list and detail view with the option of approve , reject ,notes and search option | 9 |  | 2 | Estimates considered just for API integration as approval request list will hold the approve reject action buttons | 16
|  | View created Request with Approval / Rejection (Approver 2) | page which includes list and detail view with the option of approve , reject ,notes and search option |  |  | 0 |  | 0 | Same design as Approver |  | Same as approver 1 flow | 12
|  | Manage Quotation | List view | [6 empty] | 10 | List view of department with search and pagination
|  |  | create/ edit/ update View | [6 empty] | 16 | Same component for create/ edit and view. 5-6 textual and drop down fields are considered with all required validations and API integration
|  |  | 2 to 3 page which includes list view,create, edit,view details,search . | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns |  | 5 | considering 2 to 3 page which includes list view,create, edit,view details,search . It will similar layouts for all the pages | 6 |  |  |  | 16 | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns
|  | Manage Payment | List view | [6 empty] | 10 | List view of department with search and pagination
|  |  | create/ edit/ update View | [6 empty] | 16 | Same component for create/ edit and view. 5-6 textual and drop down fields are considered with all required validations and API integration
|  |  | Invoice create and download | [6 empty] | 16 | Need to look for suitable library which will convert html to pdf and download the invoice. If invoice creation is handle in backend then this task will not take time
|  |  | Integrate Payment gateway | [6 empty] | 8 | use and test payment gateway module integrated in backend
|  |  | Manage Invoice and Receiptwere user can view list view, detail of payment and reciept generation of payment |  |  | 6 | considering 3 to 4 page were user can view list view, detail of payment and reciept generation of payment | 9 |  |  |  | 24
|  | Terms of Engagement | List view | [6 empty] | 10 | List view of department with search and pagination
|  |  | create/ edit/ update View | [6 empty] | 16 | Same component for create/ edit and view. 5-6 textual and drop down fields are considered with all required validations and API integration. Email integration is consider from backend
|  |  | User will be able to add / view the terms of engagement details.share via mail alonmg with proposal |  |  | 5 | considering 2 to 3 page as list , detail of terms which includes add, edit and search option | 7 |  |  |  | 12
|  | Evaluation Process | [9 empty] | 12
|  | Valuation Instructor Screen | View detail page with the status of valuation |  |  | 3 | considering detail page with the status of valuation | 5 |  | 6 | Details screen with 4 fields and all required validation | 12
|  | Site Description Screen | List view | [6 empty] | 10 | List view of department with search and pagination
|  |  | create/ edit/ update View | [6 empty] | 16 | Same component for create/ edit and view. 5-6 textual and drop down fields are considered with all required validations and API integration
|  |  | User will be able to create / edit/ view /delete the site description details. |  |  | 2 | considering the same design manage department with change in data | 5 |  |  |  | 12
|  | Comparable Evidences | List view | [6 empty] | 10 | List view of department with search and pagination
|  |  | create/ edit/ update View | [6 empty] | 16 | Same component for create/ edit and view. 5-6 textual and drop down fields are considered with all required validations and API integration
|  |  | User will be able to create / edit/ view /delete the evidence details and upload relevant documents |  |  | 4 | considering 2to3 page which includes list view, detail view,add,edit,delete,search and upload option | 5 |  |  |  | 12
|  | Valuation Assessment | List view | [6 empty] | 10 | List view of department with search and pagination
|  |  | create/ edit/ update View | [6 empty] | 16 | Same component for create/ edit and view. 5-6 textual and drop down fields are considered with all required validations and API integration
|  |  | User will be able to create / edit/ view /delete the assessment details and upload relevant documents |  |  | 2 | considering the same design manage department with change in data | 5 |  |  |  | 12
|  | Relevant Documents | List view | [6 empty] | 10 | List view of department with search and pagination
|  |  | create/ edit/ update View | [6 empty] | 16 | Same component for create/ edit and view. 5-6 textual and drop down fields are considered with all required validations and API integration
|  |  | User will be able to upload / view /delete the document details. |  |  | 4 | considering 2 to 3 screen where user upload, view and delete document | 5 |  |  |  | 12
|  | View valuation Request Internal Approval / Rejection | List view | [6 empty] | 10 | List view of department with search and pagination
|  |  | create/ edit/ update View | [6 empty] | 16 | Same component for create/ edit and view. 5-6 textual and drop down fields are considered with all required validations and API integration
|  |  | User will be able to view / approve / reject the valuation request details along with status and approver name / email and notes. |  |  | 4 | considering 2 to 3 screen with option of accept, reject,list and detail page | 5 |  |  |  | 12
|  | Notifications | User will be able to view the notifications related to creation approval status and other notification if any. |  |  | 2 | considered pop up for notification | 5 |  | 2 | Notification integration is considered in project setup. Here just need to capture notification based on requirement. Notification trigger will be handle from backend is considered | 24
|  | Reports | User will be able to view the 10 – 15 reports based on the process and projects. | Assuming maximum 10/12 reports with having mostly tabular data |  | 4 | considering tabular structure for report will provide only 2 in design | 9 | only 2 Reports considering other rest of similer for reuse | 32 | Reports in tabular view which will have filter, search and pagination. Report will have download to excel option. Data need to be map for each table 4-5hr for each table is considered | 60 | Assuming maximum 10/12 reports with having mostly tabular data
|  | Log out |  |  |  | 0 | amusing log out leads to login page | 0 |  | 2 | It is a simple logout | 4
4 | Others | Document Automation Works | • User will be able to upload/import document in from of PDF, JPEG, JPG, and Word formats. • We will fetch Data/Details from the uploaded documents as per certain criteria/parameters. This ensures that we will fetch selective data to the system and not the whole document as is • User will be able to view data, update data, delete data • User will be able to further extract/export selected data to PDF, CSV and Excel document format. Note: • We assume document details/data in the source format will have a predefined structure. We will consider predefined format document to be processed to further generate readable data on the system. • We will only support certain data formats for import and export - PDF, JPEG, JPG, and Word for import and PDF, CSV, Excel format for export • User will not be able to add additional fields. • Exported data will be viewed in a Tabular/Grid format. | otification |  | 12 | Considerig 6 -8 pages like view data, update data, delete data | 20 |  | 10 | Document upload option and API integration is consider here. Read data from document is considere to be handle in backend. | 60
|  | SMS Integration | [7 empty] | NA | Handle in backend | 24
|  | Email Integration | [7 empty] | NA | Hande in backend | 24
|  | English and Arabic Language | [5 empty] | 60 | Considering English and Arabiic for both, user and super admin with mobile responisve | 16 |  | 40
|  | Payment Gateway Integration | [9 empty] | 60
|  | Mobile Responisve |  |  |  | 20 | Considering 5 - 7 Unique screens only.
|  | After Inegration support | [5 empty] | 40 | After Inegration support
|  | Testing | Issues & bug fixing
|  | assets sharing |  |  |  | 8
|  | Presentation |  |  |  | 6
|  | ui guideline |  |  |  | 6
|  | Number of hours |  |  |  | 157 |  | 285 |  | 720 |  | 716
|  | Number of days |  |  |  | 19.625 |  | 35.625 |  | 90 |  | 89.5
|  | Number of weeks |  |  |  | 3.925 |  | 7.125 |  | 18 |  | 17.9

## WBS-Master
[5 empty] | Graphics |  |  | HTML |  | Frontend (Razor Forms) (.Net Core MVC) |  | (C# .NET Core API) (Rest Based) |  | MOBILE (React Native / Xamrin ) |  | Mobile (IOS) |  | Mobile (Android)
Sr. No. | Interface | Modules/Sub Modules | Features / Tasks | Assumptions | Is Unique | Estimation (Hours) | Assumptions / Remarks | Estimation (Hours) | Assumptions / Remarks | Estimation | Assumptions / Remarks | Estimation | Assumptions / Remarks | Estimations | Assumptions / Remarks | Estimations | Assumptions / Remarks | Estimations | Assumptions / Remarks
| Project Setup |  |  | As discussed with SA team, we will have service oriented architecture for this, where we will have REST based API and front end as MVC. Cutomer have plan to have mobile application in future |  | 8 | understanding | 8 | Project setup and theme setup | 40 | Setup architecture, general & common utilities for project | 60 | Setup architecture, general & common utilities for project
ERP/CRM integration is not considered in this estimation, as mentioned in scope ERP/Existing CRM integration will be in phase 2
1 | Super Admin User (Custom) | Login | User will be login into the application with given username / password. | considering 1 page with user name and password text inputs |  | 4 | considering 1 page with user name and password text inputs | 9 |  | 8 | We will have service oriented architecture, so token based system will be there | 16
|  | Forget Password |  | considerng 2 page with option of enter email and reset password |  | 4 | considerng 2 page with option of enter email and reset password |  |  | 8 |  | 12
|  | Dashboard | to view the overview of the proposal status, revenue generation, project performance, Management details, client details and analyst details. | Assuming we will have mostly tabular data & some bar / pie charts |  | 18 | considering 2 option with one iteration, No any graphcs included | 30 | to view the overview of the proposal status, revenue generation, project performance, Management details, client details and analyst details. | 18 | Assuming we will have mostly tabular data & some bar / pie charts | 24
|  | Manage Department | User will be able to create / edit/ view /active / de active the department details. There will be 5-10 text fields. and user will be able to view it | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns |  | 8 | considering 3 to 4 page as list view, detail view, where user can able to create / edit/ view /active / de active the acess permision | 15 | User will be able to create / edit/ view /active / de active the department details. There will be 5-10 text fields. and user will be able to view it | 8 | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns | 10
|  | Manage Sub Admin | User will be able to create / edit/ view /active / de active the Sub admin details. There will be 5-10 text fields. and user will be able to view it | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns |  | 5 | considering the same design manage department with change in data | 8 | considering the same design manage department with change in data | 8 | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns | 10
|  | Roles and Access Permissions | User will be able to create / edit/ view /active / de active the roles and access permission details. |  |  | 5 | considering 3 to 4 page as create / edit/ view /active / de active the acess permision | 8 |  | 12 |  | 20
| Valuation Process | Master
|  | Location | User will be able to create / edit/ view /active / de active / search the created location details. | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns |  | 8 | considering the same design manage department with change in data with cosmetic support | 5 | Using the same design super admin Manage Department 5/7 fields entry form and will have only 1/2 cascade dropdowns | 6 | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns | 8
|  | Client | User will be able to create / edit/ view /active / de active / search the client details. | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns |  |  |  | 4 | Considerign 5/7 fields entry form and will have only 1/2 cascade dropdowns | 8 | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns | 10
|  | External Vendors | User will be able to create / edit/ view /active / de active / search the created external vendor details. | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns |  |  |  | 3 | Comsidering with 5/7 fields entry form and will have only 1/2 cascade dropdowns | 8 | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns | 10
|  | Projects | User will be able to create / edit/ view /active / de active / search the created project details. | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns |  |  |  | 0 | Re-use same as above | 8 | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns | 12
|  | Valuation Approver | User will be able to create / edit/ view /active / de active / search the created valuation approver details. | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns |  |  |  | 0 | Re-use same as above | 8 | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns | 10
|  | External Valuation Approver | User will be able to create / edit/ view /active / de active / search the created external valuation approver details. | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns |  |  |  | 0 | Re-use same as above | 8 | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns | 10
|  | History | User will be able to create / edit/ view /active / de active / search the created history details. | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns |  |  |  | 0 | Re-use same as above | 8 | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns | 10
|  | Currency | User will be able to create / edit/ view /active / de active / search the currency details. | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns |  |  |  | 0 | Re-use same as above | 6 | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns | 8
|  | Approval Master | User will be able to create / edit/ view /active / de active / search the approval master details. | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns |  |  |  | 0 | Re-use same as above | 8 | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns | 10
|  | Valuation Request creation |  |  |  | 0 |  | 0 | Re-use same as above | 8 | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns | 16
|  | View created Request with Approval / Rejection (Approver 1) | page which includes list and detail view with the option of approve , reject ,notes and search option |  |  | 4 | considering 2 to 3 page which includes list and detail view with the option of approve , reject ,notes and search option | 9 |  | 8 |  | 16
|  | View created Request with Approval / Rejection (Approver 2) | page which includes list and detail view with the option of approve , reject ,notes and search option |  |  | 0 |  | 0 | Same design as Approver | 8 |  | 12
|  | Manage Quotation | 2 to 3 page which includes list view,create, edit,view details,search . | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns |  | 5 | considering 2 to 3 page which includes list view,create, edit,view details,search . It will similar layouts for all the pages | 6 |  | 8 | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns | 16 | Assuming we will have 5/7 fields entry form and will have only 1/2 cascade dropdowns
|  | Manage Payment | Manage Invoice and Receiptwere user can view list view, detail of payment and reciept generation of payment |  |  | 6 | considering 3 to 4 page were user can view list view, detail of payment and reciept generation of payment | 9 |  | 16 |  | 24
|  | Terms of Engagement | User will be able to add / view the terms of engagement details.share via mail alonmg with proposal |  |  | 5 | considering 2 to 3 page as list , detail of terms which includes add, edit and search option | 7 |  | 12 |  | 12
|  | Evaluation Process | [7 empty] | 12 |  | 12
|  | Valuation Instructor Screen | View detail page with the status of valuation |  |  | 3 | considering detail page with the status of valuation | 5 |  | 12 |  | 12
|  | Site Description Screen | User will be able to create / edit/ view /delete the site description details. |  |  | 2 | considering the same design manage department with change in data | 5 |  | 12 |  | 12
|  | Comparable Evidences | User will be able to create / edit/ view /delete the evidence details and upload relevant documents |  |  | 4 | considering 2to3 page which includes list view, detail view,add,edit,delete,search and upload option | 5 |  | 12 |  | 12
|  | Valuation Assessment | User will be able to create / edit/ view /delete the assessment details and upload relevant documents |  |  | 2 | considering the same design manage department with change in data | 5 |  | 10 |  | 12
|  | Relevant Documents | User will be able to upload / view /delete the document details. |  |  | 4 | considering 2 to 3 screen where user upload, view and delete document | 5 |  | 10 |  | 12
|  | View valuation Request Internal Approval / Rejection | User will be able to view / approve / reject the valuation request details along with status and approver name / email and notes. |  |  | 4 | considering 2 to 3 screen with option of accept, reject,list and detail page | 5 |  | 10 |  | 12
|  | Notifications | User will be able to view the notifications related to creation approval status and other notification if any. |  |  | 2 | considered pop up for notification | 5 |  | 28 |  | 24
|  | Reports | User will be able to view the 10 – 15 reports based on the process and projects. | Assuming maximum 10/12 reports with having mostly tabular data |  | 4 | considering tabular structure for report will provide only 2 in design | 9 | only 2 Reports considering other rest of similer for reuse | 60 | Assuming maximum 10/12 reports with having mostly tabular data | 60 | Assuming maximum 10/12 reports with having mostly tabular data
|  | Log out |  |  |  | 0 | amusing log out leads to login page | 0 |  | 2 |  | 4
4 | Others | Document Automation Works | • User will be able to upload/import document in from of PDF, JPEG, JPG, and Word formats. • We will fetch Data/Details from the uploaded documents as per certain criteria/parameters. This ensures that we will fetch selective data to the system and not the whole document as is • User will be able to view data, update data, delete data • User will be able to further extract/export selected data to PDF, CSV and Excel document format. Note: • We assume document details/data in the source format will have a predefined structure. We will consider predefined format document to be processed to further generate readable data on the system. • We will only support certain data formats for import and export - PDF, JPEG, JPG, and Word for import and PDF, CSV, Excel format for export • User will not be able to add additional fields. • Exported data will be viewed in a Tabular/Grid format. | otification |  | 12 | Considerig 6 -8 pages like view data, update data, delete data | 20 |  | 40 |  | 60
|  | SMS Integration | [7 empty] | 0 |  | 24
|  | Email Integration | [7 empty] | 0 |  | 24
|  | English and Arabic Language | [5 empty] | 60 | Considering English and Arabiic for both, user and super admin with mobile responisve | 40 |  | 40
|  | Payment Gateway Integration | [7 empty] | 0 |  | 60
|  | Mobile Responisve |  |  |  | 20 | Considering 5 - 7 Unique screens only.
|  | After Inegration support | [5 empty] | 40 | After Inegration support
|  | Testing | Issues & bug fixing
|  | assets sharing |  |  |  | 8
|  | Presentation |  |  |  | 6
|  | ui guideline |  |  |  | 6
|  | Number of hours |  |  |  | 157 |  | 285 |  | 478 |  | 716
|  | Number of days |  |  |  | 19.625 |  | 35.625 |  | 59.75 |  | 89.5
|  | Number of weeks |  |  |  | 3.925 |  | 7.125 |  | 11.95 |  | 17.9

## Resource Structure
# | Resource Type | No. of Resource | Weeks | Total | Given By | Approved By | Comment
1 | Graphic | 1 | 3.9 | 3.9 | varun
2 | HTML | 1 | 7.1 | 7.1 | Viren
3 | .NET MVC (Front end) | 1 | 11.9 | 11.9 | Nilesh
4 | .NET API (backend) | 1 | 17.9 | 17.9 | Nilesh |  | Service oriented architecture will be there
5 | BA | 2 | 6 | 12 | Amol
6 | Devops | 1 | 6.4 | 6.4 | Swapnil Shingote
7 | SA | 1 | 4 | 4 | Swapnil Waghela

## (Revised)EOREMAD_Gantt_Char V1
For Proposal | ravi.thokal@neosofttech.com
SDLC | Weeks / Activities | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32
Requirement Gathering | bar: W1 to W8
Devops | bar: W8 to W11; W28 to W30
Design | bar: W6 to W10
Development | bar: W10 to W25
QA - Test Plan & Test Cases | bar: W10 to W13
QA - Testing | bar: W20 to W25
UAT | bar: W26 to W28
UAT Sign off | bar: W29
Production Deployment | bar: W29 to W30
Training | bar: W31 to W32
| Weeks / Activities | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32
For Internal Purpose | Resource Loading | [32 empty] | Man Weeks
PM | PM | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 16.5
BA | BA 1 | [32 empty] | 6 | bar: W1 to W6
| BA 2 | [32 empty] | 6 | bar: W3 to W8
Graphics Designer | Designer | [32 empty] | 5 | bar: W6 to W10
TL | Architect 1 | [6 empty] | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [5 empty] | 12.5
HTML Designer | HTML Designer | [32 empty] | 8 | bar: W9 to W16
.NET Core | Dev 1 | [32 empty] | 15 | bar: W10 to W24
| Dev 2 | [32 empty] | 15 | bar: W11 to W25
QA | Manual Tester 1 | [32 empty] | 9 | bar: W17 to W25
UAT | .Net Dev 1 | [32 empty] | 3 | bar: W26 to W28
| HTML | [32 empty] | 3 | bar: W26 to W28
| Tester | [32 empty] | 3 | bar: W26 to W28
Deployment | Devops | [32 empty] | 7 | bar: W8 to W11; W28 to W30
Training | BA | [32 empty] | 2 | bar: W31 to W32
Delivery Excellence | [33 empty] | 8
| Total | [32 empty] | 119
30

## (Revised)_Gantt_chr_ Angular
For Proposal | ravi.thokal@neosofttech.com
SDLC | Weeks / Activities | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32
Requirement Gathering | bar: W1 to W8
Devops | bar: W8 to W11; W28 to W30
Design | bar: W6 to W10
Development | bar: W10 to W25
QA - Test Plan & Test Cases | bar: W10 to W13
QA - Testing | bar: W20 to W25
UAT | bar: W26 to W28
UAT Sign off | bar: W29
Production Deployment | bar: W29 to W30
Training | bar: W31 to W32
| Weeks / Activities | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32
For Internal Purpose | Resource Loading | [32 empty] | Man Weeks
PM | PM | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 16.5
BA | BA 1 | [32 empty] | 6 | bar: W1 to W6
| BA 2 | [32 empty] | 6 | bar: W3 to W8
Graphics Designer | Designer | [32 empty] | 5 | bar: W6 to W10
TL | Architect 1 | [6 empty] | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [5 empty] | 12.5
HTML Designer | HTML Designer | [32 empty] | 8 | bar: W9 to W16
Angular | Dev1 | [32 empty] | 11 | bar: W15 to W25
| Dev2 | [32 empty] | 7 | bar: W19 to W25
.NET Core | Dev 1 | [32 empty] | 16 | bar: W10 to W25
| Dev 2 | W15: 0.5; W16: 0.5; W17: 0.5; W18: 0.5; W19: 0.5; W20: 0.5; W21: 0.5; W22: 0.5; W23: 0.5; W24: 0.5; W25: 0.5 | 5.5
QA | Manual Tester 1 | [32 empty] | 9 | bar: W17 to W25
UAT | .Net Dev 1 | [32 empty] | 3 | bar: W26 to W28
| HTML | [32 empty] | 3 | bar: W26 to W28
| Tester | [32 empty] | 3 | bar: W26 to W28
Deployment | Devops | [32 empty] | 7 | bar: W8 to W11; W28 to W30
Training | BA | [32 empty] | 2 | bar: W31 to W32
Delivery Excellence | [33 empty] | 8
| Total | [32 empty] | 128.5
30