## Slide 1
Completed Level-I of wireframes, SRS document and sent it to Karuna after working on wireframes, requirement gathering with both BA teams.
Worked on Vinod suggested wireframe changes, SRS documents.
Submitted Wireframes to Vinod & team on 12th April & got message that End client yet to review them.
Planned Key Milestones
Milestone Legend
Eltizam - Real Estate Valuation System
Planning to completed all review suggested changes on wireframes, SRS documents.
Also, planning to start Graphical & HTML once wireframes are freezes.
Once UI tech stacks finalized then, we will start CICD, SA related task in coming 1-2 weeks.
Accomplishment for the week
Status update for the week - 10th April to 14th April 2023
Phase | Planned Start date | Planned End date | Actual Start date | Actual End date
Kick-Off | 9-Mar-23 | 9-Mar-23 | 9-Mar-23 | 9-Mar-23
Req. Gather, SRS writing | 10-Mar-23 | 22-May-23 | 13-Mar-23 | 
Wireframes | 27-Mar-23 | 22-May-23 | 20-Mar-23 | 
Graphic integration | 24-Apr-23 | 24-May-23 |  | 
Themes integration | 24-Apr-23 | 23-Jun-23 |  | 
Development | 1-May-23 | 8-Sep-23 |  | 
Testing | 19-Jun-23 | 8-Sep-23 |  | 
UAT release | 11-Sep-23 | 22-Sep-23 |  | 
Production release | 25-Sep-23 | 26-Sep-23 |  | 
Training | 27-Sep-23 | 10-Oct-23 |  | 
We have submitted Wireframes, SRS document to Karuna & yet to receive feedback from Eltizam business.
Key Risks
PM : YallaReddy
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Yet to get approvals from client on completed Wireframes.
Warranty | 10-Oct-23 | 07-Nov-23 |  |