## Slide 1
We discussed Valuation and Evaluation process sub modules with BA resources on 28th April.
We started working on wireframes and SRS documents for above discussion for Evaluation process flow.
Planned Key Milestones
Milestone Legend
Eltizam - Real Estate Valuation System
We will work on SRS document, wireframes Evaluation process left over sub modules.
Also, continue working on Valuation process sub modules which discussed on 28th April.
Also, planning to start Graphical & HTML once wireframes are freezes in coming weeks. This is needs to be discussed on high priority with Vinod and team.
Accomplishment for the week
Status update for the week - 2nd May to 5th May 2023
Phase | Planned Start date | Planned End date | Actual Start date | Actual End date
Kick-Off | 9-Mar-23 | 9-Mar-23 | 9-Mar-23 | 9-Mar-23
Req. Gather, SRS writing | 10-Mar-23 | 22-May-23 | 13-Mar-23 | 
Wireframes | 27-Mar-23 | 22-May-23 | 20-Mar-23 | 
Graphic integration | 24-Apr-23 | 24-May-23 |  | 
Themes integration | 24-Apr-23 | 23-Jun-23 |  | 
Development | 1-May-23 | 8-Sep-23 |  | 
Testing | 19-Jun-23 | 8-Sep-23 |  | 
UAT release | 11-Sep-23 | 22-Sep-23 |  | 
Production release | 25-Sep-23 | 26-Sep-23 |  | 
Training | 27-Sep-23 | 10-Oct-23 |  | 
Received feedback on wireframes from Eltizam team but yet to get confirmations from End client.
Discussed Evaluation process modules with Karuna and BA completed almost all wireframes.
Key Risks
PM : YallaReddy
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Need to receive final feedback on wireframes from End-client.
Needs to discuss timeline delay with Vinod and team.
Warranty | 10-Oct-23 | 07-Nov-23 |  |