## Slide 1
Received signoff email to start design, development only for master modules.
Pulled UI/UX designer to start design phase.
Planned Key Milestones
Milestone Legend
Eltizam - Real Estate Valuation System
Will start design of UI/UX for the project.
Also, keep in touch with BA to get final requirements on Evaluation module.
We will start HTML design after requirements finalized to avoid rework.
Accomplishment for the week
Status update for the week - 10th to 14th July, 2023
Phase | Planned Start date | Planned End date | Actual Start date | Actual End date
Kick-Off | 9-Mar-23 | 9-Mar-23 | 9-Mar-23 | 9-Mar
Requirement Gathering | 10-Mar-23 | 22-May-23 | 13-Mar-23 | 
Wireframes | 27-Mar-23 | 22-May-23 | 20-Mar-23 | 
SRS Document | 1-May-23 | 26-May-23 | 23-May23 | 
Graphic integration | 24-Apr-23 | 24-May-23 |  | 
Themes integration | 24-Apr-23 | 23-Jun-23 |  | 
Development | 1-May-23 | 8-Sep-23 |  | 
Testing | 19-Jun-23 | 8-Sep-23 |  | 
UAT release | 11-Sep-23 | 22-Sep-23 |  | 
Production release | 25-Sep-23 | 26-Sep-23 |  | 
Training | 27-Sep-23 | 10-Oct-23 |  | 
Warranty | 10-Oct-23 | 07-Nov-23 |  | 
All wireframes & SRS-I document were submitted.
Still waiting for Evaluation process requirement changes.
Key Risks
PM : YallaReddy
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Need to receive final feedback on wireframes from End-client.
As of now, project is delayed by 7 weeks, so please do needful by giving reviews on wireframes.