## Slide 1
Design phase is going on with master modules.
Completed and submitted login, user screens for review.
Working on Resource, Location, Roles, system user master module design.
Planned Key Milestones
Milestone Legend
Eltizam - Real Estate Valuation System
Will do design of UI/UX for the projectt on other pages.
Also, keep in touch with BA to get final requirements on Evaluation module.
Will submit master modules by mid of next week and continue on Evaluation process design.
Accomplishment for the week
Status update for the week - 24th to 28th July, 2023
Phase | Planned Start date | Planned End date | Actual Start date | Actual End date
Kick-Off | 9-Mar-23 | 9-Mar-23 | 9-Mar-23 | 9-Mar
Requirement Gathering | 10-Mar-23 | 22-May-23 | 13-Mar-23 | 
Wireframes | 27-Mar-23 | 22-May-23 | 20-Mar-23 | 
SRS Document | 1-May-23 | 26-May-23 | 23-May23 | 
Graphic integration | 24-Apr-23 | 24-May-23 | 17-Jul-2023 | 
Themes integration | 24-Apr-23 | 23-Jun-23 |  | 
Development | 1-May-23 | 8-Sep-23 |  | 
Testing | 19-Jun-23 | 8-Sep-23 |  | 
UAT release | 11-Sep-23 | 22-Sep-23 |  | 
Production release | 25-Sep-23 | 26-Sep-23 |  | 
Training | 27-Sep-23 | 10-Oct-23 |  | 
Warranty | 10-Oct-23 | 07-Nov-23 |  | 
Needs to get Evaluation process requirement final changes.
Started design for master modules, completed 4 screens & submitted login, user screens.
Key Risks
PM : YallaReddy
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Need to receive final feedback on wireframes from End-client.
As of now, project is delayed by 8 weeks, so please do needful by giving reviews on wireframes & finish final requirements.