## Slide 1
Designer completed Admin role Dashboard changes and completed them & submitted to client.
No work from BA team here as completed all areas.
Took feedback with Karuna on design pages & looks great for them.
Planned Key Milestones
Milestone Legend
Eltizam - Real Estate Valuation System
We are expecting signoff on design, SRS documents in next week. So, that we will start development.
Lets take management call with Eltizam and NeoSOFT to discuss immediate action to speed-up development process if no update comes.
Accomplishment for the week
Status update for the week - 21st Aug to 25th Aug, 2023
Phase | Planned Start date | Planned End date | Actual Start date | Actual End date
Kick-Off | 9-Mar-23 | 9-Mar-23 | 9-Mar-23 | 9-Mar
Requirement Gathering | 10-Mar-23 | 22-May-23 | 13-Mar-23 | 
Wireframes | 27-Mar-23 | 22-May-23 | 20-Mar-23 | 
SRS Document | 1-May-23 | 26-May-23 | 23-May23 | 
Graphic integration | 24-Apr-23 | 24-May-23 | 17-Jul-23 | 
Themes integration | 24-Apr-23 | 23-Jun-23 |  | 
Development | 1-May-23 | 8-Sep-23 |  | 
Testing | 19-Jun-23 | 8-Sep-23 |  | 
UAT release | 11-Sep-23 | 22-Sep-23 |  | 
Production release | 25-Sep-23 | 26-Sep-23 |  | 
Training | 27-Sep-23 | 10-Oct-23 |  | 
Warranty | 10-Oct-23 | 07-Nov-23 |  | 
Project Kick-off started on 9th March 2023
Requirement Gathering & documentation work started from 10th Mar 2023.
Designer started from 17th July & pages are almost done except Dashboards
Key Risks
PM : YallaReddy
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Need to receive final feedback on wireframes, SRS from End-client.
As of now, project is delayed by 10 weeks, so please do needful by giving reviews on wireframes & finish final requirements.