## Slide 1
Worked on wireframes, requirement gathering with both BA teams.
Yet to receive confirmations from Karuna regarding first review on wireframes.
Requirement Gathering session – 4 have planned and executed.
Effort Summary
Planned Key Milestones
Milestone Legend
Real Estate Valuation Management System
We will get feedback changes from Karuna on Monday next week.
We will work on reviewed changes from Eltizam team.
Accomplishment for the week
Status update for the week - 27th March to 31st March 2023
Phase | MIS Start date | MIS End date | Actual Start date | Actual End date
Kick-Off | 9-Mar-23 | 9-Mar-23 | 9-Mar-23 | 9-Mar-23
Req. gathering | 13-Mar-2023 |  | 13-Mar-2023 | 
Wireframes | 20-Mar-2023 |  | 20-Mar-2023 | 
We have submitted Wireframes, SRS document to Karuna
Also, taking regular calls with Eltizam team regarding status
Key Risks
PM : YallaReddy
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Total Effort : 1875
Effort burnt this week : 26
Effort burnt till date : 94
Resources
PM : 1
BA : 1
Dev : 0
Arct : 0
Tester: 0
Waiting for approval or review from Eltizam team