## Slide 1
We discussed Valuation and Evaluation process sub modules with BA resources on 28th April.
We started working on wireframes and SRS documents for above discussion.
Planned Key Milestones
Milestone Legend
Eltizam - Real Estate Valuation System
We will work on SRS document, wireframes Evaluation process sub modules.
Also, continue working on Valuation process sub modules which discussed today.
Also, planning to start Graphical & HTML once wireframes are freezes in coming weeks.
Accomplishment for the week
Status update for the week - 24th April to 28th April 2023
Phase | Planned Start date | Planned End date | Actual Start date | Actual End date
Kick-Off | 9-Mar-23 | 9-Mar-23 | 9-Mar-23 | 9-Mar-23
Req. Gather, SRS writing | 10-Mar-23 | 22-May-23 | 13-Mar-23 | 
Wireframes | 27-Mar-23 | 22-May-23 | 20-Mar-23 | 
Graphic integration | 24-Apr-23 | 24-May-23 |  | 
Themes integration | 24-Apr-23 | 23-Jun-23 |  | 
Development | 1-May-23 | 8-Sep-23 |  | 
Testing | 19-Jun-23 | 8-Sep-23 |  | 
UAT release | 11-Sep-23 | 22-Sep-23 |  | 
Production release | 25-Sep-23 | 26-Sep-23 |  | 
Training | 27-Sep-23 | 10-Oct-23 |  | 
Received feedback on wireframes from Eltizam team but yet to get confirmations from End client.
Discussed Evaluation process modules with Karuna and started working on them.
Key Risks
PM : YallaReddy
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Need to receive final feedback on wireframes from End-client.
Warranty | 10-Oct-23 | 07-Nov-23 |  |