## Slide 1
We discussed Valuation and Evaluation process sub modules with BA resources on 28th April.
We finished all wireframes and waiting for the feedback from end client team.
Planned Key Milestones
Milestone Legend
Eltizam - Real Estate Valuation System
We will get end client feedback on mid of next week mostly.
Needs to start writing SRS document once wireframes finalized and signoff from client.
Also, planning to start Graphical & HTML once wireframes are freezes in coming weeks. We needs to be discuss project timeline with Vinod and team on high priority.
Accomplishment for the week
Status update for the week - 8th May to 12th May 2023
Phase | Planned Start date | Planned End date | Actual Start date | Actual End date
Kick-Off | 9-Mar-23 | 9-Mar-23 | 9-Mar-23 | 9-Mar-23
Requirement Gathering | 10-Mar-23 | 22-May-23 | 13-Mar-23 | 
Wireframes | 27-Mar-23 | 22-May-23 | 20-Mar-23 | 
SRS Document | 1-May-23 | 26-May-23 |  | 
Graphic integration | 24-Apr-23 | 24-May-23 |  | 
Themes integration | 24-Apr-23 | 23-Jun-23 |  | 
Development | 1-May-23 | 8-Sep-23 |  | 
Testing | 19-Jun-23 | 8-Sep-23 |  | 
UAT release | 11-Sep-23 | 22-Sep-23 |  | 
Production release | 25-Sep-23 | 26-Sep-23 |  | 
Training | 27-Sep-23 | 10-Oct-23 |  | 
Warranty | 10-Oct-23 | 07-Nov-23 |  | 
Received feedback on wireframes from Eltizam team but yet to get confirmations from End client.
Discussed Evaluation process modules with Karuna and BA completed almost all wireframes.
Key Risks
PM : YallaReddy
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Need to receive final feedback on wireframes from End-client.
Needs to discuss timeline delay with Vinod and team.