## Slide 1
We finished all module wireframes and waiting for the feedback from end client team.
Also, started writing SRS documents to master module. Currently, we are on Users, Role and permissions master SRS documents.
Planned Key Milestones
Milestone Legend
Eltizam - Real Estate Valuation System
Hope, we will get end client feedback on wireframes by 25th or 26th May.
If any changes from feedback comes then, we will work on wireframe too.
Yet to start design integrations once master SRS submitted, reviewed from client.
Accomplishment for the week
Status update for the week - 22nd May to 26th May, 2023
Phase | Planned Start date | Planned End date | Actual Start date | Actual End date
Kick-Off | 9-Mar-23 | 9-Mar-23 | 9-Mar-23 | 9-Mar-23
Requirement Gathering | 10-Mar-23 | 22-May-23 | 13-Mar-23 | 
Wireframes | 27-Mar-23 | 22-May-23 | 20-Mar-23 | 
SRS Document | 1-May-23 | 26-May-23 |  | 
Graphic integration | 24-Apr-23 | 24-May-23 |  | 
Themes integration | 24-Apr-23 | 23-Jun-23 |  | 
Development | 1-May-23 | 8-Sep-23 |  | 
Testing | 19-Jun-23 | 8-Sep-23 |  | 
UAT release | 11-Sep-23 | 22-Sep-23 |  | 
Production release | 25-Sep-23 | 26-Sep-23 |  | 
Training | 27-Sep-23 | 10-Oct-23 |  | 
Warranty | 10-Oct-23 | 07-Nov-23 |  | 
Received feedback on submitted wireframes from Eltizam but yet to get final confirmations.
Started writing SRS documents on master modules from last week.
Key Risks
PM : YallaReddy
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Need to receive final feedback on wireframes from End-client.
Needs to discuss timeline delay with Vinod and team. As of now, project is delayed by 3 weeks.