## Slide 1
We finished all module wireframes and waiting for the feedback from end client team.
Also, started writing SRS documents to master module. More than half of the master modules SRS documents are preparing.
Planned Key Milestones
Milestone Legend
Eltizam - Real Estate Valuation System
We yet to final signoff on submitted wireframes and its delayed by 3 weeks as of now..
If any changes from feedback comes then, we will work on wireframe too.
Will submit 1st draft of the SRS document on Master modules.
Accomplishment for the week
Status update for the week - 29th May to 2nd June, 2023
Phase | Planned Start date | Planned End date | Actual Start date | Actual End date
Kick-Off | 9-Mar-23 | 9-Mar-23 | 9-Mar-23 | 9-Mar
Requirement Gathering | 10-Mar-23 | 22-May-23 | 13-Mar-23 | 
Wireframes | 27-Mar-23 | 22-May-23 | 20-Mar-23 | 
SRS Document | 1-May-23 | 26-May-23 | 23-May23 | 
Graphic integration | 24-Apr-23 | 24-May-23 |  | 
Themes integration | 24-Apr-23 | 23-Jun-23 |  | 
Development | 1-May-23 | 8-Sep-23 |  | 
Testing | 19-Jun-23 | 8-Sep-23 |  | 
UAT release | 11-Sep-23 | 22-Sep-23 |  | 
Production release | 25-Sep-23 | 26-Sep-23 |  | 
Training | 27-Sep-23 | 10-Oct-23 |  | 
Warranty | 10-Oct-23 | 07-Nov-23 |  | 
Received feedback on submitted wireframes from Eltizam but yet to get final confirmations.
Started writing SRS documents on master modules and half of them are done.
Key Risks
PM : YallaReddy
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Need to receive final feedback on wireframes from End-client.
As of now, project is delayed by 3 weeks, so please do needful by giving reviews on wireframes.