## Slide 1
We finished all module wireframes and waiting for the feedback from end client team on Evaluation process modules.
Submitted SRS-I document to Karuna after call and they are looking into final changes.
Also, continue writing SRS-I for Evaluation process modules and targeting for next week.
Yet to get approval email from client to start design from our side.
Planned Key Milestones
Milestone Legend
Eltizam - Real Estate Valuation System
We will continue writing SRS document on pending Evaluation process modules & to submit complete SRS document.
Will get mostly signoff on master modules and start design phase.
Will discuss Currency master with client team after internal discuss.
Accomplishment for the week
Status update for the week - 12th June to 16th June, 2023
Phase | Planned Start date | Planned End date | Actual Start date | Actual End date
Kick-Off | 9-Mar-23 | 9-Mar-23 | 9-Mar-23 | 9-Mar
Requirement Gathering | 10-Mar-23 | 22-May-23 | 13-Mar-23 | 
Wireframes | 27-Mar-23 | 22-May-23 | 20-Mar-23 | 
SRS Document | 1-May-23 | 26-May-23 | 23-May23 | 
Graphic integration | 24-Apr-23 | 24-May-23 |  | 
Themes integration | 24-Apr-23 | 23-Jun-23 |  | 
Development | 1-May-23 | 8-Sep-23 |  | 
Testing | 19-Jun-23 | 8-Sep-23 |  | 
UAT release | 11-Sep-23 | 22-Sep-23 |  | 
Production release | 25-Sep-23 | 26-Sep-23 |  | 
Training | 27-Sep-23 | 10-Oct-23 |  | 
Warranty | 10-Oct-23 | 07-Nov-23 |  | 
All wireframes were submitted and waiting for final confirmation on Evaluation process modules.
Submitted SRS-I document on Master modules and continuing on other modules..
Key Risks
PM : YallaReddy
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Need to receive final feedback on wireframes from End-client.
As of now, project is delayed by 3-4 weeks, so please do needful by giving reviews on wireframes.