## Slide 1
Yet to get approval email on master modules from client to start design from our side.
Planned Key Milestones
Milestone Legend
Eltizam - Real Estate Valuation System
Scheduling call with team to discuss next steps to taken care to make things smooth and proper.
Yet to get signoffs on submitted wireframes but as per Karuna confirmation, Evaluation process will change.
Hoping to have discussion on new changes from business on pending modules from next week.
Accomplishment for the week
Status update for the week - 3rd to 7th July, 2023
Phase | Planned Start date | Planned End date | Actual Start date | Actual End date
Kick-Off | 9-Mar-23 | 9-Mar-23 | 9-Mar-23 | 9-Mar
Requirement Gathering | 10-Mar-23 | 22-May-23 | 13-Mar-23 | 
Wireframes | 27-Mar-23 | 22-May-23 | 20-Mar-23 | 
SRS Document | 1-May-23 | 26-May-23 | 23-May23 | 
Graphic integration | 24-Apr-23 | 24-May-23 |  | 
Themes integration | 24-Apr-23 | 23-Jun-23 |  | 
Development | 1-May-23 | 8-Sep-23 |  | 
Testing | 19-Jun-23 | 8-Sep-23 |  | 
UAT release | 11-Sep-23 | 22-Sep-23 |  | 
Production release | 25-Sep-23 | 26-Sep-23 |  | 
Training | 27-Sep-23 | 10-Oct-23 |  | 
Warranty | 10-Oct-23 | 07-Nov-23 |  | 
All wireframes were submitted and waiting for final confirmation on Evaluation process modules.
Submitted SRS-I document on Master modules and continuing on Evaluation process document.
Key Risks
PM : YallaReddy
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Need to receive final feedback on wireframes from End-client.
As of now, project is delayed by 6-7 weeks, so please do needful by giving reviews on wireframes.