## Slide 1
Design phase for master modules is completed and submitted to Karuna & team.
Working on design for Requestor, Approver modules & also received feedback from Karuna for master modules.
BA team is writing SRS document for Evaluation process for the clarified area.
Planned Key Milestones
Milestone Legend
Eltizam - Real Estate Valuation System
Will do design of UI/UX for the projectt on pending pages.
Will design module wise as they submits for review & also, will work on feedback changes in design.
Will continue writing SRS document and targeting to finish next week except open items.
Targeting to complete both SRS and Design things by next week.
Accomplishment for the week
Status update for the week - 31st Jul to 4th Aug, 2023
Phase | Planned Start date | Planned End date | Actual Start date | Actual End date
Kick-Off | 9-Mar-23 | 9-Mar-23 | 9-Mar-23 | 9-Mar
Requirement Gathering | 10-Mar-23 | 22-May-23 | 13-Mar-23 | 
Wireframes | 27-Mar-23 | 22-May-23 | 20-Mar-23 | 
SRS Document | 1-May-23 | 26-May-23 | 23-May23 | 
Graphic integration | 24-Apr-23 | 24-May-23 | 17-Jul-2023 | 
Themes integration | 24-Apr-23 | 23-Jun-23 |  | 
Development | 1-May-23 | 8-Sep-23 |  | 
Testing | 19-Jun-23 | 8-Sep-23 |  | 
UAT release | 11-Sep-23 | 22-Sep-23 |  | 
Production release | 25-Sep-23 | 26-Sep-23 |  | 
Training | 27-Sep-23 | 10-Oct-23 |  | 
Warranty | 10-Oct-23 | 07-Nov-23 |  | 
Working on design phase & submitted master modules.
Started writing SRS document for Evaluation module.
Key Risks
PM : YallaReddy
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Need to receive final feedback on wireframes from End-client.
As of now, project is delayed by 8 weeks, so please do needful by giving reviews on wireframes & finish final requirements.