## Slide 1
Design for modules i.e., Requestor, Valuer, Approver role Evaluation process are done and submitted this week.
Also, worked on reviewed changes from client as well & completed.
BA team submitted SRS document for Requestor, Approver are done and submitted.
Discussed open items with Karuna and changed SRS as per confirmations.
Planned Key Milestones
Milestone Legend
Eltizam - Real Estate Valuation System
Will work on Dashboard changes and completes 3 days.
Will continue to work on SRS document for Valuer module which is final one.
Will submit design pages next week & finish SRS too.
Lets take management call with Eltizam and NeoSOFT to discuss immediate action to speed-up development process.
Accomplishment for the week
Status update for the week - 7th Aug to 11th Aug, 2023
Phase | Planned Start date | Planned End date | Actual Start date | Actual End date
Kick-Off | 9-Mar-23 | 9-Mar-23 | 9-Mar-23 | 9-Mar
Requirement Gathering | 10-Mar-23 | 22-May-23 | 13-Mar-23 | 
Wireframes | 27-Mar-23 | 22-May-23 | 20-Mar-23 | 
SRS Document | 1-May-23 | 26-May-23 | 23-May23 | 
Graphic integration | 24-Apr-23 | 24-May-23 | 17-Jul-23 | 
Themes integration | 24-Apr-23 | 23-Jun-23 |  | 
Development | 1-May-23 | 8-Sep-23 |  | 
Testing | 19-Jun-23 | 8-Sep-23 |  | 
UAT release | 11-Sep-23 | 22-Sep-23 |  | 
Production release | 25-Sep-23 | 26-Sep-23 |  | 
Training | 27-Sep-23 | 10-Oct-23 |  | 
Warranty | 10-Oct-23 | 07-Nov-23 |  | 
Project Kick-off started on 9th March 2023
Requirement Gathering & documentation work started from 10th Mar 2023.
Designer started from 17th July & pages are almost done except Dashboards
Key Risks
PM : YallaReddy
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Need to receive final feedback on wireframes, SRS from End-client.
As of now, project is delayed by 8 weeks, so please do needful by giving reviews on wireframes & finish final requirements.