## Slide 1
In this week, we received signoff on submitted SRS, design pages from Vinod via email.
On 31st Aug, too a call with Karuna & comes to know we can start project from next week.
Planned Key Milestones
Milestone Legend
Eltizam - Real Estate Valuation System
As we received signoff on masters, design pages we will start development.
Will take internal call & update you regarding dates on development to client team.
Accomplishment for the week
Status update for the week - 25th Aug to 01st Sept, 2023
Phase | Planned Start date | Planned End date | Actual Start date | Actual End date
Kick-Off | 09-03-23 | 9-03-23 | 9-03-23 | 9-03-23
Requirement Gathering | 10-03-23 | 22-05-23 | 13-03-23 | 11-8-23
Wireframes | 27-03-23 | 22-05-23 | 20-03-23 | 11-8-23
SRS Document | 01-05-23 | 26-05-23 | 23-05-23 | 23-8-23
Graphic integration | 24-Apr-23 | 24-05-23 | 17-07-23 | 23-8-23
Themes integration | 24-Apr-23 | 23-Jun-23 |  | 
Development | 1-May-23 | 8-Sep-23 |  | 
Testing | 19-Jun-23 | 8-Sep-23 |  | 
UAT release | 11-Sep-23 | 22-Sep-23 |  | 
Production release | 25-Sep-23 | 26-Sep-23 |  | 
Training | 27-Sep-23 | 10-Oct-23 |  | 
Warranty | 10-Oct-23 | 07-Nov-23 |  | 
Kick-off on 9th March 2023, Requirement Gathering & documentation work started from 10th Mar 2023 & completed it on 23rd Aug.
Designer started from 17th July & submitted all design on 23rd Aug.
Key Risks
PM : YallaReddy
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
As of now, project is delayed by 12 weeks due to delay in initial phase of RG.