## Slide 1
We have on boarded HTML developer on Friday & he is going to through the wireframes.
Also, architecture was prepared for API which will be given developers.
Planned Key Milestones
Milestone Legend
Eltizam - Real Estate Valuation System
We will start developing HTML Pages by referring design pages.
Also, we will start development of website too.
Accomplishment for the week
Status update for the week - 4th Sept to 8th Sept, 2023
Phase | Planned Start date | Planned End date | Actual Start date | Actual End date
Kick-Off | 09-03-23 | 9-03-23 | 9-03-23 | 9-03-23
Requirement Gathering | 10-03-23 | 22-05-23 | 13-03-23 | 11-8-23
Wireframes | 27-03-23 | 22-05-23 | 20-03-23 | 11-8-23
SRS Document | 01-05-23 | 26-05-23 | 23-05-23 | 23-8-23
Graphic integration | 24-Apr-23 | 24-05-23 | 17-07-23 | 23-8-23
Themes integration | 24-Apr-23 | 23-Jun-23 | 08-09-23 | 
Development | 1-May-23 | 8-Sep-23 | 11-09-23 | 
Testing | 19-Jun-23 | 8-Sep-23 |  | 
UAT release | 11-Sep-23 | 22-Sep-23 |  | 
Production release | 25-Sep-23 | 26-Sep-23 |  | 
Training | 27-Sep-23 | 10-Oct-23 |  | 
Warranty | 10-Oct-23 | 07-Nov-23 |  | 
Kick-off on 9th March 2023, Requirement Gathering from 10th Mar to 23rd Aug.
Designer started from 17th July & submitted all design on 23rd Aug.
HTML integration started from 8th Sept 2023.
Key Risks
PM : YallaReddy
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
As of now, project is delayed by 12 weeks due to delay in initial phase of RG.