## Slide 1
HTML Developer integrated changes into .NET application for Resource master.
API team worked on master modules Backend changes and 85% master modules are done.
Working on integrating HTML design into pages of .NET application.
Planned Key Milestones
Milestone Legend
Eltizam - Real Estate Valuation System
Will continue working on HTML development this week as well.
Will work on HTML design changes migration into .NET & call APIs for the same pages.
Accomplishment for the week
Status update for the week - 25th Sept to 29th Sept, 2023
Phase | Planned Start date | Planned End date | Actual Start date | Actual End date
Kick-Off | 09-03-23 | 9-03-23 | 9-03-23 | 9-03-23
Requirement Gathering | 10-03-23 | 22-05-23 | 13-03-23 | 11-8-23
Wireframes | 27-03-23 | 22-05-23 | 20-03-23 | 11-8-23
SRS Document | 01-05-23 | 26-05-23 | 23-05-23 | 23-8-23
Graphic integration | 24-Apr-23 | 24-05-23 | 17-07-23 | 23-8-23
Themes integration | 24-Apr-23 | 23-Jun-23 | 11-09-23 | 
Development | 1-May-23 | 8-Sep-23 | 13-09-23 | 
Testing | 19-Jun-23 | 8-Sep-23 |  | 
UAT release | 11-Sep-23 | 22-Sep-23 |  | 
Production release | 25-Sep-23 | 26-Sep-23 |  | 
Training | 27-Sep-23 | 10-Oct-23 |  | 
Warranty | 10-Oct-23 | 07-Nov-23 |  | 
Kick-off on 9th March 2023, Requirement Gathering from 10th Mar to 23rd Aug.
Designer started from 17th July & submitted all design on 23rd Aug.
HTML integration & .NET Development started from 13th Sept 2023.
We have completed 85% master modules at this moment from API level.
Key Risks
PM : YallaReddy
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
As of now, project is delayed by 12 weeks due to delay in initial phase of RG.